## Sheet1
Activity | Task | Owner | Start Week | Duration (Weeks) | End Week
Activity 1: Conceptual & Logical Design | Collect functional & non-functional requirements | Nguyen Van Duy Anh | 1 | 1 | 1
Activity 1: Conceptual & Logical Design | Draw ER Diagram | Nguyen Van Duy Anh | 1 | 2 | 2
Activity 1: Conceptual & Logical Design | Normalize schema to 3NF | Nguyen Van Duy Anh | 2 | 1 | 2
Activity 1: Conceptual & Logical Design | Draft initial DDL scripts | Duong Hien Chi Kien | 2 | 1 | 2
Activity 2: Physical Implementation | Create database & tables | Nguyen Van Duy Anh | 3 | 1 | 3
Activity 2: Physical Implementation | Create indexes & Define views | Nguyen Van Duy Anh | 3 | 1 | 3
Activity 2: Physical Implementation | Seed synthetic data & Define API endpoints | Tran Anh Chuong | 3 | 2 | 4
Activity 3: Verification & Validation | Test referential integrity & constraints | Tran Anh Chuong | 4 | 1 | 4
Activity 3: Verification & Validation | Validate business rules & edge cases | All members | 4 | 1 | 4
Activity 4: Performance Testing | Analyze query patterns | Duong Hien Chi Kien | 5 | 1 | 5
Activity 4: Performance Testing | Add/refine indexes & Partitioning strategy | Nguyen Van Duy Anh | 5 | 1 | 5
Activity 5: Final Presentation | Finalize report & Prepare slides | Duong Hien Chi Kien | 6 | 1 | 6
Activity 5: Final Presentation | Rehearse presentation & Demo | All members | 6 | 1 | 6